## Tuntilista
Tuntilista
Nimi | Piia
Toteutuneet pvm | Vaihe | Osatehtävä | Sunnitellut tunnit | Toteutuneet tunnit | Erotus
2019-06-03 | Project Management | Project Plan | 1 | 1 | 0
2019-06-05 | Project Management | Project Presentation | 0.5 | 0.5 | 0
2019-06-07 | Website | Setting up Tomcat | 1 | 1.5 | 0.5
2019-06-07 | Website | Testing out JSP | 1 | 1 | 0
2019-06-09 | Project Management | Deadlines / Milestones | 0.5 | 0.5 | 0
2019-06-10 | Design | Frontpage Prototype | 1.5 | 1.5 | 0
2019-06-12 | Researching Java | JSP Tutorials | 1 | 1 | 0
2019-06-13 | Experimenting with JSP | Navbar, Image Slideshow | 0.5 | 1 | 0.5
2019-06-14 | Creating the Frontpage | CSS (Banner, Boxes) & HTML | 2 | 2 | 0
2019-06-16 | Creating the Frontpage | Image Slideshow | 2 | 4 | 2
2019-06-17 | Creating the Frontpage | Image Slideshow - Trying to find a Solution | 1 | 3.5 | 2.5
2019-06-17 | Researching Angular | Angular CLI Installation, Angular Tutorials | 2 | 3 | 1
2019-06-18 | Researching Angular | Tutorials and Experimentation | 2 | 4 | 2
2019-06-20 | Creating the Frontpage | Including Angular Material and Tutorials | 3 | 3 | 0
2019-06-21 | Researching Angular | Angular Material and Routing Tutorials | 3 | 2.5 | -0.5
2019-06-22 | Creating Anime and Contact Page | Designing Anime Page and Routing | 3 | 3 | 0
2019-06-23 | Researching Databases | MySQL, AWS, MongoDB, lowdb | 2 | 2 | 0
2019-06-24 | Contact Page | Creating the Design | 1 | 1 | 0
2019-06-26 | Logo | Creation and Implementation | 2 | 2 | 0
2019-07-01 | Researching Databases + Tutorials | MongoDB, lowdb | 3 | 3 | 0
2019-07-02 | Researching MongoDB + Tutorials | MongoDB Atlas, mlab | 2 | 3 | 1
2019-07-03 | Experimenting with MongoDB | MEAN Stack Tutorials and Implementation | 3 | 3 | 0
2019-07-04 | Testing MongoDB | Postman, Get Data | 1 | 1.5 | 0.5
2019-07-06 | Setting up the MongoDB Database | Watching Tutorials and Creating Schema | 4 | 2.5 | -1.5
2019-07-08 | Setting up the MongoDB Database | Watching Tutorials and Creating a User Schema | 4 | 2 | -2
2019-07-09 | Setting up the Backend | server.js, api - register and login | 2 | 2 | 0
2019-07-12 | Angular Authentication | Research, Tutorials, Implementation | 2 | 2 | 0
2019-07-13 | Angular Authentication | Creating the Register Component & Service | 2 | 2 | 0
2019-07-14 | Angular Authentication | Register and Login Page, Connecting to the DB | 1 | 2.5 | 1.5
2019-07-15 | Angular Authentication & CSS | Registering Users, Implementation of my Font and Carousel | 3 | 3.5 | 0.5
2019-07-17 | Setting up the Posts Pages | Creating the mongoDB collection, Creating Anime Reviews | 2 | 2 | 0
2019-07-18 | Connecting Anime Review Page with DB | Connecting the different Components, Getting the DB Data | 2 | 3.5 | 1.5
2019-07-21 | Continuing Anime Review Page | Displaying single Posts, Selecting Posts | 3 | 3 | 0
2019-07-22 | Posting Anime Reviews from the Page | Post Data to the DB from Anime Reviews Page | 4 | 4 | 0
2019-07-23 | Posting Anime Reviews from the Page | Finishing the Posting and Select Feature | 4 | 4 | 0
2019-07-24 | Creating the Blog and Games Review Pages | DB, Get Data, Post Data, CSS, HTML | 3 | 3 | 0
2019-07-25 | Finishing Touches on the Posts and Reviews | Graphics (Stars & Dog Paws), Colors | 1 | 1.5 | 0.5
2019-07-26 | Finishing the Blog | Finishing CSS and Texts | 2 | 2 | 0
2019-07-27 | Hosting the Blog | Trying Firebase and Heroku, Hosting the Backend on Heroku | 1 | 3 | 2
2019-07-28 | Hosting the Blog, Writing End Report | Trying Heroku, Hosting the Frontend (Angular App) on Firebase | 2 | 4 | 2
|  |  | 81 | 95 | 14