## Project-Milestone Plan
Project-Milestone Plan
Milestone | Date
Project start | 2019-06-03
Design Prototype (Frontpage) | 2019-06-12
Decision to continue with Java: Yes or No? | 2019-06-17
Blog finished | 2019-07-26
Presentation | Week 32
Final report | Week 32
Project End | Week 32