## Tuntilista
Tuntilista
Nimi | Piia
Toteutuneet pvm | Vaihe | Osatehtävä | Sunnitellut tunnit | Toteutuneet tunnit | Erotus
2019-06-03 | Project Management | Project Plan | 1 | 1 | 0
2019-06-05 | Project Management | Project Presentation | 0.5 | 0.5 | 0
2019-06-07 | Website | Setting up Tomcat | 1 | 1.5 | 0.5
2019-06-07 | Website | Testing out JSP | 1 | 1 | 0
2019-06-09 | Project Management | Deadlines / Milestones | 0.5 | 0.5 | 0
2019-06-10 | Design | Frontpage Prototype | 1.5 | 1.5 | 0
2019-06-12 | Researching Java | JSP Tutorials | 1 | 1 | 0
2019-06-13 | Experimenting with JSP | Navbar, Image Slideshow | 0.5 | 1 | 0.5
2019-06-14 | Creating the Frontpage | CSS (Banner, Boxes) & HTML | 2 | 2 | 0
2019-06-16 | Creating the Frontpage | Image Slideshow | 2 | 4 | 2
2019-06-17 | Creating the Frontpage | Image Slideshow - Trying to find a Solution | 1 | 3.5 | 2.5
2019-06-17 | Researching Angular | Angular CLI Installation, Angular Tutorials | 2 | 3 | 1
2019-06-18 | Researching Angular | Tutorials and Experimentation | 2 | 4 | 2
2019-06-20 | Creating the Frontpage | Including Angular Material and Tutorials | 3 | 3 | 0
2019-06-21 | Researching Angular | Angular Material and Routing Tutorials | 3 | 2.5 | -0.5
2019-06-22 | Creating Anime and Contact Page | Designing Anime Page and Routing | 3 | 3 | 0
2019-06-23 | Researching Databases | MySQL, AWS, MongoDB, lowdb | 2 | 2 | 0
2019-06-24 | Contact Page | Creating the Design | 1 | 1 | 0
2019-06-26 | Logo | Creation and Implementation | 2 | 2 | 0
0
0
0
0
0
0
0
0
0
|  |  | 30 | 38 | 8